Timeline of Cuadrilla’s operation at Becconsall

27th July 2010	Cuadrilla submits application 08/10/0973 for an exploratory borehole and testing of hydrocarbons

20th October 2010	Lancashire County Council approves application 08/10/0973. Work to be completed within 18 months of commencement and conditions include an ecological method statement to protect wintering birds

4th February 2011	Ecological method statement for application 08/10/0973 (see update of 30th August 2011)

22nd February 2011	Lease signed between Reaper Ltd and Keith Bond for shooting rights on land at Banks Marsh for three years, starting on 1st February 2011-up to 31st January 2014

28th March 2011	Cuadrilla’s development begins at Becconsall

17th August 2011	Letter from Phil Mason, Cuadrilla, to Jonathan Haine/Rob Jones of LCC, that drilling will start on 22nd August 2011

30th August 2012	Update by Ecology Services to Cuadrilla on bird surveys – refers to method statement but no detail about mitigation

19th September 2012	Cuadrilla submits application 08/12/1032 to extend well testing and restoration until 28th March 2014

27th September 2012	Cuadrilla fails to restore the Becconsall site by the scheduled restoration deadline set under conditions for application 08/10/0973

22nd October 2012	Letter from Dr Sarah Manchester, Senior Planning Officer (Ecology) at LCC, that Cuadrilla has not submitted enough information about the impacts on wintering birds to make a decision.

29th October 2012	Kate Willshaw, of Natural England, email to Rob Jones, of LLC says the application does not provide enough information about impacts on wintering birds

6th June 2013	Letter from Phil Mason, for Cuadrilla, to LCC planners requesting amendment to application 08/12/1032 to include reservoir diagnostics programme and extend restoration until 28th September 2014. Letter refers to talks with local landowners about field management as mitigation for loss of bird winter grazing in 2013-2014.

10th July 2013	Email from Claire Storey, of Natural England, to Rob Jones, LLC planner, objecting to application 08/12/1032 on grounds	of lack of information

15th July 2013	Group of maps by Cuadrilla, submitted to LCC, including one which shades fields later leased.

16th July 2013	Cuadrilla signs agreement with Reaper Ltd permitting the use of lands north of Marsh Road to maintain in a suitable condition for wintering birds from 31st October 2013-31st March 2014 as a condition of amended application 08/10/0973

16th July 2013	Cuadrilla signs agreement with Robert Ball and Sons, Hundred End Farm, J Sephton, Bonny Banks Farm, and Bill Johnson, Marshfield Farm, for use of lands north of Marsh Road, for same period and purpose

18th July 2013	Report by Ecology Services (Report of Winter Bird Surveys) for Cuadrilla, recommending “management of an area of land within and adjacent to the Marsh Farm Fields BHS”.

23rd July 2013	Email Mark Oldridge, of Cuadrilla, to Rob Jones, LCC planner, attaching additional information “to cover concerns expressed by Dr Sarah Manchester your county ecologist and Claire Storey on behalf of Natural England”. It refers to proposed mitigation measures.

14th October 2013	Letter from Stuart Perigo, LCC, to Phil Mason, Cuadrilla Resource, saying LCC requires an EIA before it will consider application 08/12/1032 and indicates mitigation on impact on wintering wildlife has not been approved.

22nd January 2014	Lease signed between Reaper Ltd and Keith Bond for shooting rights at Banks Marsh for three years, starting on 1st February 2014

24th March 2014	Letter from Patrick Waring, Ecology Services, to Mr C Hird, Development Management, Cuadrilla, on recommendations for bird mitigation, including no shooting, daily wardening and provision of food

27th March 2014	Cuadrilla’s new planning application LCC/2014/0047 received and validated by Lancashire County Council for three-year permission to carry out pressure monitoring, followed by plugging and abandonment

17th April 2014	Email from LCC ecologist, Sarah Manchester, to LCC planning officer, Rob Jones, which says mitigation including supplementary feeding, were being progressed under earlier application “but it is not clear whether these were/are being implemented as part of the current proposals”

1st May 2014	Email from Kate Berry, Natural England, to LCC planning officer, Rob Jones, asking whether proposed mitigation is in addition to that already in place, what is the location of additional fields and are agreements in place.

20th June 2014	Ecology Services submits report of winter bird surveys to Arup

22nd September 2014	Letter from Phil Mason, of Cuadrilla, to Stuart Perigo, of LCC, withdrawing application 08/12/1032

23rd September 2014	LCC planning committee approves application LCC/2014/0047 but does not issue permission

14th November 2014	Letter from Francis Egan to Stuart Perigo, LCC planner, confirms replacement land agreements are being secured and will be in place up to 31st March 2015

1st May 2015	LCC issues the decision notice and publishes it on the council’s website as planning officers prepared to begin the May bank holiday. There are no details of the Section 106 agreement on the council website. A note says: “Due to the size of the S106 agreement that accompanies this decision. It is not possible to display the document today it will appear here shortly”