## ALL
1 July 2016 licence changes
REL - licence to terminate
1-2 yrs - Extension where licensee needs additional time to meet requirements of licence
RA* - Licensee requested 2014 Model Clause conversion and Retention Area agreed
Partial relinquishments - see on interactive map
(www.gov.uk/guidance/oil-and-gas-onshore-maps-and-gis-shapefiles#interactive-map)
Licence | Operator | Change | Extension time or New Model Clause Retention Area Work Programme
PEDL126 | UKOG | RA | submit a Field Development Plan for the Markwells Wood 1 discovery by 30 June 2017
PEDL162 | Ineos | 2 yrs | Two year extension to Initial Term
PEDL163 | IGas | 2 yrs | Two year extension to Second Term
PEDL164 | Aurora | 2 yr | Two year extension to Initial Term
PEDL165 | Cuadrilla | RA | three retention areas: RA1-North - collect outcrop data and interpret existing 2D seismic data by January 2018, to acquire gravity and/or magnetic geophysical data by 30 June 2019 and to apply for planning permission to drill a well by 30 June 2021, RA2-Central - drill and hydraulically fracture a horizontal well by 30 June 2019 and to submit a Field Development Plan by 30 June 2021, RA3-South - acquire gravity and/or magnetic geophysical data by 30 June 2019 and to apply for planning permission to drill a well by 30 June 2021. Partial Relinquishment of 63 km2 was made.
PEDL169 | IGAS/Alkane | RA/DA | complete new seismic acquisition by 30 June 2019, submit planning permission to drill a well by 30 June 2021/Markham Main Coal Mine Vent Field
PEDL173 | IGas | REL | Licence Ended
PEDL174 | IGas | REL | Licence Ended
PEDL178 | IGas | REL | Licence Ended
PEDL179 | IGAS | REL | Licence Ended
PEDL183 | Rathlin | RA | Two retention areas - RA1 - drill a well to 2000m and test by 30 June 2018 and to complete geotechnical studies by 30 June 2019, RA2 - acquire and interpret 15km2 new 3D seismic data by 30 June 2018 and to complete geotechnical studies by 30 June 2019. Partial relinquishment of 263 km2 was made.
PEDL184 | IGas | RA | reprocess regional geomagnetic data by 30 June 2017, sample and reinterpret Namurian shale from Gronant borehole by 30 March 2018, acquire new seismic data by 30 June 2019 and drill a well by 30 June 2021
PEDL185 | IGas | REL | Licence Ended
PEDL186 | IGas | REL | Licence Ended
PEDL187 | IGas | REL | Licence Ended
PEDL188 | IGas | RA | acquire new 2D seismic data by 30 June 2020 and drill a well by 30 June 2021
PEDL189 | IGas | 2 yr | Two year extension to Initial Term
PEDL190 | IGas | RA | reprocess of regional Geomagnetic data by 30 June 2017 and drill a well by 30 June 2019
PEDL191 | Egdon | RA | integrate reprocessed 2D data and regional geochemical analysis of offset well by 31 December 2017, submit planning application for a well by 31 December 2019 and drill a well by 30 June 2021
PEDL193 | INEOS | RA | acquire new seismic data by 30 June 2018, submit planning application to drill a well by 30 June 2020, and drill, hydraulically fracture and flow test a well by 30 June 2021
PEDL200 | IGas | RA | drill one well by 31 December 2017, acquire new seismic data by 31 December 2019 and drill a horizontal well by June 2021
PEDL201 | Egdon | RA | submit a planning application for a well by 31 June 2019 and drill a well by 30 June 2021
PEDL202 | Egdon/Alkane | RA/DA | submit a planning application for a well by 30th June 2019 and drill a well by 30th June 2021/Calverton Coal Mine Vent Field
PEDL204 | Hutton | 2 yr | Two year extension to Initial Term, partial relinquishment of 70 km2 was made
PEDL207 | IGas | REL | Licence Ended
PEDL208 | Hutton | REL | Licence Ended
PEDL209 | Egdon | RA | integrate the results of Laughton 1 well by 30 June 2017, submit planning application for a well by 31 December 2019 and drill a well by 30 June 2021
PEDL210 | IGas | RA | acquire new seismic data by 31 December 2018, submit planning application to drill a well by 31 December 2020 and drill a well by 30 June 2021
PEDL214 | U.K. Onshore | 2yrs | Two year extension to Initial Term, partial relinquishment of 74 km2 was made
PEDL215 | U.K. Onshore | 2yrs | Two year extension to Initial Term, partial relinquishment of 60 km2 was made
PEDL216 | U.K. Onshore | 2yrs | Two year extension to Initial Term, partial relinquishment of 22 km2 was made
PEDL217 | U.K. Onshore | 2yrs | Two year extension to Initial Term, partial relinquishment of 41 km2 was made
PEDL219 | U.K. Onshore | REL | Licence Ended
PEDL220 | U.K. Onshore | REL | Licence Ended
PEDL224 | Sonorex | 1 yr | One year extension to Initial Term, Partial relinquishment of 39 km2 was made
PEDL231 | Celtique | REL | Licence Ended
PEDL233 | IGAS | 2 yrs | Two year extension to Initial Term
PEDL234 | Celtique | 2 yr | Two year extension to Initial Term
PEDL235 | IGAS | 2 yrs | Two year extension to Initial Term
PEDL237 | Egdon | REL | Licence Ended
PEDL241 | Egdon | 1 yr | One year extension to Initial Term
PEDL243 | Celtique | REL | Licence Ended
PEDL244 | Cuadrilla | RA | flow test the Balcombe 2z well by 30 June 2019 and drill one well by 30 June 2021
PEDL246 | Horse Hill Development | RA | acquire new 3D seismic by 30 June 2017, drill Horse Hill 1 sidetrack by 30 September 2017
PEDL253 | Egdon | 1 yr | One year extension to Initial Term
PEDL254 | Hutton | 2 yr | Two year extension to Initial Term
*New Model Clauses were laid in 2014 (see http://www.legislation.gov.uk/uksi/2014/1686/contents/made). Several licensees have asked for existing licences to be amended so as to incorporate these new Model Clauses. The 2014 Model Clauses implemented certain changes from previous Model Clauses: principally that the retention of acreage is made subject to the agreement of Retention and Development Areas (clauses 16, 19 and 43), there is a reduced confidentiality period for certain information about hydraulic fracturing (clause 32) and Clause 5(3)(b) may modify the condition relating to a surrender of 50% of the initial Licensed Area where Retention Areas or Development Areas exist.